## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2019
2020
Total Duration
Dive into the Research Domain
Proposal submission
Research and Experiments
Library design and implementation
Library Testing and Reimplementation
Completion and Final Report
Today
Dec
2020
Feb
Mar
Apr
May
Jun
Dec 10
Read and understand the context of the Problem
Dec 20
Dec 21
Go through previous arts and create Bibliography
Dec 31
Jan 1
Feb 24
Go deep and Analyze selected previous arts
Narrow down and define the Research Problem
Feb 24 - Feb 25
Choose a methodology for the experiment
Feb 26 - Feb 27
Define appropriate measurements for experiment
Feb 28 - Mar 7
Proposal and Proposal Presentation Preparation
Mar 8 - Mar 29
Extracting features
Mar 29 - Apr 7
Prioritizing features
Apr 23 - Apr 29
Group the features for functions
Apr 30 - May 6
Design the Library of functions
May 31 - Jul 17
Implement the Library (mid evaluation)
Jul 18 - Aug 6
Evaluate the functions
Oct 6 - Oct 16
Reimplementation of the Library
Oct 17 - Oct 26
Aug 10
Final Report
Oct 26
Oct 27
Final Presentation
Nov 16
Aug 7
Oct 6
Implement the Library (finalevaluation)
Apr 8
Evaluating impact of the feature
Apr 22
Set the features into classes
May 7 - May 31
Jul
Aug
Sep
Oct
Nov
Dec 10
-
Nov 16
Mid Evaluation
Aug 6
Final Evaluation
Oct 26
Sign Off
Nov 16
Kick Off
Dec 10